## BOQ
BOQ Progress Payment Certificate with Deductions
Enter contract quantities, rates and cumulative executed quantities; the sheet works out the certificate value, deductions and net
Item | Description | Unit | Contract qty | Unit rate | Contract amount | Previous cum. qty | Current cum. qty | % done | This period qty | Value to date | Previous value | This period value
1.1 | General excavation for foundations | m³ | 450 | 18 |  | 450 | 450
1.2 | Compacted backfill | m³ | 300 | 22 |  | 180 | 255
2.1 | Plain concrete | m³ | 40 | 380 |  | 40 | 40
2.2 | Reinforced concrete | m³ | 260 | 520 |  | 143 | 202.8
2.3 | Reinforcement steel | ton | 30 | 2600 |  | 16.5 | 23.4
2.4 | Formwork | m² | 1500 | 48 |  | 825 | 1200
3.1 | Blockwork 20 cm | m² | 1900 | 62 |  | 570 | 1045
3.2 | Internal and external plaster | m² | 4200 | 28 |  | 420 | 1260
3.3 | Floor tiles | m² | 1100 | 85 |  | 0 | 110
3.4 | Paint | m² | 4800 | 16 |  | 0 | 0
4.1 | Electrical points | point | 320 | 140 |  | 64 | 112
4.2 | Plumbing points | point | 120 | 190 |  | 24 | 48
4.3 | Aluminium windows | m² | 210 | 520 |  | 0 | 52.5
4.4 | Doors | no. | 36 | 780 |  | 0 | 0
Total
Yellow: current quantity exceeds the contract quantity (over-measure, needs a variation). Red: current quantity is lower than the previous one.

## Certificate
Payment certificate
BOQ Progress Payment Certificate with Deductions
Contract data
Certificate no. | 4
Contract start date | 2026-01-10
Contract duration (days) | 365
Valuation date | 2026-08-31
Contract value and work
Original contract value
Approved variations (net) | 15000
Revised contract value
Work executed to date (from BOQ)
Variation work executed to date | 6000
Approved materials on site (value) | 40000
Allowed percentage of materials | 80%
Gross value to date
Deductions
Retention rate % | 10%
Retention cap % of revised contract | 5%
Retention to date
Advance payment paid | 150000
Advance recovered to date (pro rata to progress)
Liquidated damages to date | 0
Other deductions | 0
Net amount due
Net certified to date
Previously certified | 205000
Net of this certificate before VAT
VAT rate | 15%
VAT amount
Amount payable incl. VAT
Indicators
Financial progress
Time elapsed
Status
Items above contract quantity

## Guide
How to use: BOQ Progress Payment Certificate with Deductions
Sheetaky.com · Ready Excel sheets in Arabic and English
What is this sheet?
The sheet prepares a main-contractor payment certificate from a bill of quantities: you enter contract quantities and rates and the cumulative executed quantities, and it works out work to date and for the period, then applies variations, materials on site, retention and its cap, advance recovery and damages, and gives the net certificate, VAT and amount payable.
Steps
1 | In the "BOQ" sheet enter the contract items (description, unit, quantity, rate) and the previous and current cumulative quantities for each.
2 | In the "Certificate" sheet enter variations, materials on site, retention rate and cap, advance payment and damages.
3 | Enter the total certified previously to get the net of this certificate and the amount payable.
4 | Check the colours: yellow for a quantity above the contract, red for one below the previous quantity.
Color legend
Input cell: type or choose your value here (blue text on yellow).
Calculated cell: automatic formula, protected from accidental edits.
Table and section headers.
Important notes
• | The calculation is cumulative: deductions are worked on the total to date and the previously certified amount is then subtracted, so retention is not deducted twice.
• | Advance recovery here is pro rata to progress; edit the formula if your contract states another method.
• | The sheet does not replace your contract conditions (FIDIC or other); check the payment and retention clauses in it.
• | Sheets are protected without a password to keep formulas safe. To unprotect: Review → Unprotect Sheet.
• | The data shown is a worked example. Clear it and type your own data in the yellow cells only.
• | More free sheets in Arabic and English at Sheetaky.com