## Cash Flow
Contract Cash Flow and Payments: Advance, Retention and Peak Funding
Enter contract value, duration and progress curve; get monthly certificates, cash in, cash out and peak working capital
|  |  | Peak funding needed (SAR) |  |  |  | Month of peak deficit |  |  |  | Financing cost (SAR) |  |  |  | Curve
Contract data | [14 empty] | Linear
Contract value (ex VAT) | 4500000 | SAR | [12 empty] | S-curve
Duration (months, up to 24) | 14 | mo | Total certified incl. VAT | [11 empty] | Front-loaded
Advance payment | 10% |  | Expected profit before financing | [11 empty] | Back-loaded
Retention per certificate | 10% |  | Profit after financing
Retention cap (of contract) | 5% |  | Total retention withheld
Defects period (months) to release | 12 | mo | Check
VAT | 15% |  | Total collected ex VAT
Client payment lag (months) | 2 | mo
Contractor cost (of contract) | 86%
Cost payment lag (months) | 1 | mo
Annual financing rate | 8%
Progress curve | S-curve
Start date | 2026-11-01
VAT and percentages are examples; check your contract and local regulations.
Monthly schedule
Month | Date | # | Cum. % | Monthly % | Certified | Advance recovery | Retention held | Retention released | Net | VAT | Cash in (ex VAT) | Cost paid | Net cash | Cumulative
|  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36

## Guide
How to use: Contract cash flow
Sheetaky.com · Ready Excel sheets in Arabic and English
What is this sheet?
Builds monthly certificates, advance, retention and VAT, the contractor cash in and out, then peak funding and its cost.
Steps
1 | Enter contract value, duration and start date and pick a progress curve.
2 | Set advance, retention, VAT and the payment lag.
3 | Enter your cost share and supplier payment lag.
4 | Read peak funding, its month and financing cost, and try another curve.
Color legend
Input cell: type or choose your value here (blue text on yellow).
Calculated cell: automatic formula, protected from accidental edits.
Table and section headers.
Important notes
• | Maximum duration 24 months; the table runs 36 months to release retention.
• | The S-curve is closest to reality on most projects.
• | A simplified financial estimate, not tax or financial advice.
• | Sheets are protected without a password to keep formulas safe. To unprotect: Review → Unprotect Sheet.
• | The data shown is a worked example. Clear it and type your own data in the yellow cells only.
• | More free sheets in Arabic and English at Sheetaky.com