## Project
Project Performance Tracker – Earned Value (EVM)
Is the project on budget and on schedule? CPI, SPI and estimate at completion
Project data
Project name |  | Residential villa project
Status date |  | 2026-10-15
Activities
# | Activity | Budget BAC | Planned % | Actual % | Actual cost AC | Planned PV | Earned EV | CV = EV−AC | SV = EV−PV | CPI | SPI
1 | Excavation & backfill | 45000 | 100% | 100% | 47000 | 45000 | 45000 | -2000 | 0 | 0.95745 | 1
2 | Reinforced concrete | 320000 | 100% | 95% | 335000 | 320000 | 304000 | -31000 | -16000 | 0.90746 | 0.95
3 | Blockwork | 85000 | 90% | 80% | 70000 | 76500 | 68000 | -2000 | -8500 | 0.97143 | 0.88889
4 | Electrical works | 120000 | 60% | 45% | 50000 | 72000 | 54000 | 4000 | -18000 | 1.08 | 0.75
5 | Plumbing | 90000 | 50% | 50% | 46000 | 45000 | 45000 | -1000 | 0 | 0.97826 | 1
6 | Plastering | 60000 | 30% | 10% | 7000 | 18000 | 6000 | -1000 | -12000 | 0.85714 | 0.33333
7 | Finishes | 280000 | 0% | 0% | 0 | 0 | 0 | 0 | 0
8 | [5 empty] | 0 | 0 | 0 | 0
9 | [5 empty] | 0 | 0 | 0 | 0
10 | [5 empty] | 0 | 0 | 0 | 0
11 | [5 empty] | 0 | 0 | 0 | 0
12 | [5 empty] | 0 | 0 | 0 | 0
13 | [5 empty] | 0 | 0 | 0 | 0
14 | [5 empty] | 0 | 0 | 0 | 0
15 | [5 empty] | 0 | 0 | 0 | 0
16 | [5 empty] | 0 | 0 | 0 | 0
17 | [5 empty] | 0 | 0 | 0 | 0
18 | [5 empty] | 0 | 0 | 0 | 0
19 | [5 empty] | 0 | 0 | 0 | 0
20 | [5 empty] | 0 | 0 | 0 | 0
21 | [5 empty] | 0 | 0 | 0 | 0
22 | [5 empty] | 0 | 0 | 0 | 0
23 | [5 empty] | 0 | 0 | 0 | 0
24 | [5 empty] | 0 | 0 | 0 | 0
25 | [5 empty] | 0 | 0 | 0 | 0
| Total | 1000000 | 57.65% | 52.2% | 555000 | 576500 | 522000 | -33000 | -54500 | 0.94054 | 0.90546
Performance indicators
Cost performance index CPI |  | 0.94054 | Above 1 = under budget
Schedule performance index SPI |  | 0.90546 | Above 1 = ahead of schedule
Estimate at completion EAC |  | 1063218.3908 | BAC ÷ CPI
Estimate to complete ETC |  | 508218.3908 | EAC − AC
Variance at completion VAC |  | -63218.3908 | Negative = expected overrun
To-complete performance TCPI |  | 1.0742 | Efficiency needed to finish within budget
Percent complete |  | 52.2% | EV ÷ BAC
Percent spent |  | 55.5% | AC ÷ BAC
Status |  | Over budget · Behind schedule

## Guide
How to use: Project Performance Tracker – Earned Value (EVM)
Sheetaky.com · Ready Excel sheets in Arabic and English
What is this sheet?
The sheet applies earned value management: for each activity you enter its budget, planned and actual percent and actual cost, and it calculates PV, EV, CV, SV, CPI and SPI, then the estimate at completion and the project status.
Steps
1 | Enter the project name and the status date.
2 | For each activity enter its approved budget (BAC).
3 | Enter the planned percent to the status date (from the schedule) and the actual percent complete.
4 | Enter the actual cost spent on each activity to date.
5 | Read the indicators: CPI below 1 means cost overrun, SPI below 1 means delay.
Color legend
Input cell: type or choose your value here (blue text on yellow).
Calculated cell: automatic formula, protected from accidental edits.
Table and section headers.
Important notes
• | Update weekly or monthly the same way so you can compare performance over time.
• | Sheets are protected without a password to keep formulas safe. To unprotect: Review → Unprotect Sheet.
• | The data shown is a worked example. Clear it and type your own data in the yellow cells only.
• | More free sheets in Arabic and English at Sheetaky.com