## Equipment Log
Heavy Equipment Log: Cost, Utilisation, Maintenance and Insurance Alerts
Log each machine with dates and cost; get daily cost, utilisation and alerts for service and insurance expiry
|  |  |  | Active machines |  | Rented |  |  | Avg utilisation |  |  | Cost to date (SAR) |  |  | Alerts |  |  |  | Type
Settings | [18 empty] | Excavator
Report date |  | 2026-10-23 | [16 empty] | Loader
Diesel price (SAR/L) |  | 0.66 |  | Cost by equipment type | [7 empty] | Note | [6 empty] | Crane
Service alert (days before) |  | 14 | [16 empty] | Concrete pump
Insurance alert (days before) |  | 30 | [16 empty] | Compressor
Generator
Truck
Scaffolding
Other
Register | [18 empty] | Ownership
Equipment | Type | Ownership | Supplier | Rate/day | Start | End | Days on site | Working days | Utilis. | Rental cost | Fuel (L) | Fuel cost | Operator/day | Total | Next service | Insurance end | Status | Alert | Owned
Komatsu PC200 excavator | Excavator | Rented | Rajhi Equipment Co. | 1100 | 2026-08-14 |  |  | 62 |  |  | 3600 |  | 250 |  | 2026-10-03 | 2027-02-20 | Working |  | Rented
Caterpillar 950 loader | Loader | Rented | Rajhi Equipment Co. | 900 | 2026-08-29 |  |  | 40 |  |  | 1800 |  | 220 |  | 2026-11-04 | 2027-05-11 | Idle
8-ton tower crane | Crane | Rented | Gulf Cranes | 2500 | 2026-09-08 |  |  | 38 |  |  | 0 |  | 400 |  | 2026-10-28 | 2027-01-21 | Working |  | Status
Concrete pump | Concrete pump | Rented | East Pumps | 1800 | 2026-09-23 | 2026-09-28 |  | 5 |  |  | 300 |  | 220 |  | 2026-09-13 | 2026-12-22 | Returned |  | Working
Air compressor | Compressor | Owned | - | 150 | 2026-07-25 |  |  | 55 |  |  | 900 |  | 0 |  | 2026-12-02 | 2026-11-17 | Working |  | Idle
250 kVA generator | Generator | Owned | - | 300 | 2026-07-15 |  |  | 90 |  |  | 5200 |  | 0 |  | 2026-10-31 | 2027-06-20 | Working |  | Breakdown
Tipper truck | Truck | Rented | City Haulage | 650 | 2026-08-24 |  |  | 48 |  |  | 2400 |  | 200 |  | 2026-11-14 | 2027-03-22 | Idle |  | Returned
Steel scaffolding set | Scaffolding | Rented | Kingdom Scaffolding | 120 | 2026-08-04 |  |  | 80 |  |  | 0 |  | 0 |  | 2027-01-21 | 2027-08-19 | Working
Bobcat mini excavator | Excavator | Rented | Contractors Arm | 700 | 2026-09-28 |  |  | 14 |  |  | 700 |  | 200 |  | 2026-10-26 | 2026-12-07 | Breakdown
Small concrete mixer | Other | Owned | - | 60 | 2026-06-25 |  |  | 70 |  |  | 0 |  | 0 |  | 2026-11-27 | 2027-04-21 | Working
Total

## Guide
How to use: Equipment log
Sheetaky.com · Ready Excel sheets in Arabic and English
What is this sheet?
Logs owned and rented heavy equipment, computes cost and utilisation and alerts for service and insurance expiry.
Steps
1 | Enter report date, diesel price and alert periods.
2 | Log each machine: type, ownership, supplier, daily rate and start date.
3 | Update working days, litres, service and insurance dates regularly.
4 | Read the alerts, cost and utilisation.
Color legend
Input cell: type or choose your value here (blue text on yellow).
Calculated cell: automatic formula, protected from accidental edits.
Table and section headers.
Important notes
• | For owned machines enter an estimated daily rate.
• | Utilisation below 50% is shaded so you can review the rental case.
• | Leave the end date blank for a machine still working.
• | Sheets are protected without a password to keep formulas safe. To unprotect: Review → Unprotect Sheet.
• | The data shown is a worked example. Clear it and type your own data in the yellow cells only.
• | More free sheets in Arabic and English at Sheetaky.com