## Risk Register
Project Risk Register: Scoring, Heat Map, Expected Value and Response
Log risks and score probability and impact; get the heat map, top risks, expected value and the suggested contingency
[9 empty] | Open risks | High + critical |  | Expected value (SAR) |  | After mitigation (SAR) |  |  |  |  | Category
Settings | [18 empty] | Schedule
Report date |  | 2026-10-23 | [16 empty] | Cost
Low up to ≤ |  | 4 | [16 empty] | Quality
Medium up to ≤ |  | 9 | Open risk heat map (probability × impact) | [5 empty] | Top 5 open risks | [9 empty] | Safety
High up to ≤ |  | 15 | Prob. \ Impact | 1 | 2 | 3 | 4 | 5 | [10 empty] | Contract
Score = probability × impact (1 to 5). Above the last limit is critical. |  |  | 5 | [15 empty] | Supply chain
|  |  | 4 | [15 empty] | Design
|  |  | 3 | [15 empty] | External
2
|  |  | 1 | [15 empty] | Response
Avoid
Mitigate
Transfer
Accept
Status
Open
Risk register | [18 empty] | Mitigating
# | Risk description | Category | Owner | Prob. | Impact | Score | Rating | Response | Mitigation action | Cost impact | Prob. % | Expected value | Status | Action due | Resid. P | Resid. I | Resid. score | Resid. EMV | Closed
R01 | Steel delivery delay and price rise | Supply chain | Contracts manager | 4 | 4 |  |  | Mitigate | Fix price early with a supplier and order in batches | 95000 |  |  | Mitigating | 2026-11-04 | 3 | 3
R02 | Owner changes to architectural drawings | Schedule | Project manager | 4 | 4 |  |  | Mitigate | Freeze design and price change orders | 60000 |  |  | Mitigating | 2026-11-12 | 3 | 2 |  |  | Rating
R03 | Shortage of skilled labour in peak season | Schedule | Site engineer | 3 | 4 |  |  | Mitigate | Contract two backup subcontractors and incentives | 40000 |  |  | Open | 2026-10-31 | 2 | 3 |  |  | Low
R04 | Heavy rain delaying concrete pours | Schedule | Project manager | 3 | 3 |  |  | Accept | Schedule float and protective covers | 25000 |  |  | Open | 2026-11-22 | 3 | 2 |  |  | Medium
R05 | Fall from height during structure works | Safety | Procurement | 2 | 5 |  |  | Mitigate | Edge protection, training and daily inspection | 150000 |  |  | Mitigating | 2026-10-28 | 1 | 5 |  |  | High
R06 | Defects in column concrete | Quality | QS | 2 | 4 |  |  | Mitigate | Cube tests and pour supervision | 70000 |  |  | Open | 2026-11-06 | 1 | 4 |  |  | Critical
R07 | Municipality approval delay | Contract | Site engineer | 4 | 3 |  |  | Transfer | Early submission and weekly follow-up | 30000 |  |  | Mitigating | 2026-11-02 | 3 | 2
R08 | Electrical subcontractor financial failure | Contract | Site engineer | 2 | 4 |  |  | Transfer | Performance bond and direct supplier payment | 80000 |  |  | Open | 2026-11-17 | 1 | 3 |  |  | Owner
R09 | MEP drawing clashes | Design | Project manager | 4 | 3 |  |  | Mitigate | 3D coordination before execution | 45000 |  |  | Mitigating | 2026-11-07 | 2 | 2 |  |  | Project manager
R10 | Cement price volatility | Supply chain | Site engineer | 3 | 3 |  |  | Accept | Bulk early purchase | 20000 |  |  | Open | 2026-12-02 | 2 | 2 |  |  | Site engineer
R11 | Change order dispute | Contract | HSE officer | 3 | 4 |  |  | Transfer | Written record of each change | 55000 |  |  | Open | 2026-11-10 | 2 | 3 |  |  | QS
R12 | Material damage from poor storage | Supply chain | QS | 2 | 2 |  |  | Mitigate | Covered store and receiving log | 15000 |  |  | Closed | 2026-10-18 | 1 | 1 |  |  | Procurement
HSE officer
Contracts manager
[19 empty] | Prob. | Prob. %
[19 empty] | 1 | 10%
[19 empty] | 2 | 30%
[19 empty] | 3 | 50%
[19 empty] | 4 | 70%
[19 empty] | 5 | 90%

## Guide
How to use: Risk register
Sheetaky.com · Ready Excel sheets in Arabic and English
What is this sheet?
Logs risks, scores them by probability and impact and shows the heat map, top risks and expected cost before and after mitigation.
Steps
1 | Enter the report date and score limits.
2 | Log each risk with category, owner and probability and impact from 1 to 5.
3 | Enter the estimated cost impact and the mitigation action and date.
4 | Re-score after mitigation and watch the residual value.
Color legend
Input cell: type or choose your value here (blue text on yellow).
Calculated cell: automatic formula, protected from accidental edits.
Table and section headers.
Important notes
• | Probability percentages per level (10% to 90%) in the right-hand list are editable.
• | Closed risks turn grey and leave the totals.
• | Expected value = cost impact × probability; an indicator, not a guarantee.
• | Sheets are protected without a password to keep formulas safe. To unprotect: Review → Unprotect Sheet.
• | The data shown is a worked example. Clear it and type your own data in the yellow cells only.
• | More free sheets in Arabic and English at Sheetaky.com