## S-Curve
Project S-Curve & Cash Flow
Compare planned, earned and actual cost month by month with an automatic S-curve chart
Settings
Project start month |  | 2026-01-01
Monthly flow
# | Month | Planned this month | Earned this month | Actual cost this month | Cumulative PV | Cumulative EV | Cumulative AC | Planned % | Earned % | EV − PV
1 | 2026-01-01 | 20000 | 18000 | 19000 | 20000 | 18000 | 19000 | 1.818% | 1.636% | -2000
2 | 2026-02-01 | 45000 | 40000 | 43000 | 65000 | 58000 | 62000 | 5.909% | 5.273% | -7000
3 | 2026-03-01 | 80000 | 72000 | 76000 | 145000 | 130000 | 138000 | 13.18% | 11.82% | -15000
4 | 2026-04-01 | 120000 | 110000 | 118000 | 265000 | 240000 | 256000 | 24.09% | 21.82% | -25000
5 | 2026-05-01 | 160000 | 150000 | 158000 | 425000 | 390000 | 414000 | 38.64% | 35.45% | -35000
6 | 2026-06-01 | 180000 | 165000 | 176000 | 605000 | 555000 | 590000 | 55% | 50.45% | -50000
7 | 2026-07-01 | 170000 |  |  | 775000 |  |  | 70.45%
8 | 2026-08-01 | 140000 |  |  | 915000 |  |  | 83.18%
9 | 2026-09-01 | 100000 |  |  | 1015000 |  |  | 92.27%
10 | 2026-10-01 | 60000 |  |  | 1075000 |  |  | 97.73%
11 | 2026-11-01 | 25000 |  |  | 1100000 |  |  | 100%
12 | 2026-12-01 |  |  |  | 1100000 |  |  | 100%
13 | 2027-01-01 |  |  |  | 1100000 |  |  | 100%
14 | 2027-02-01 |  |  |  | 1100000 |  |  | 100%
15 | 2027-03-01 |  |  |  | 1100000 |  |  | 100%
16 | 2027-04-01 |  |  |  | 1100000 |  |  | 100%
17 | 2027-05-01 |  |  |  | 1100000 |  |  | 100%
18 | 2027-06-01 |  |  |  | 1100000 |  |  | 100%
19 | 2027-07-01 |  |  |  | 1100000 |  |  | 100%
20 | 2027-08-01 |  |  |  | 1100000 |  |  | 100%
21 | 2027-09-01 |  |  |  | 1100000 |  |  | 100%
22 | 2027-10-01 |  |  |  | 1100000 |  |  | 100%
23 | 2027-11-01 |  |  |  | 1100000 |  |  | 100%
24 | 2027-12-01 |  |  |  | 1100000 |  |  | 100%
| Total | 1100000 | 555000 | 590000
Status at the last entered month
Last month with actuals |  |  | 6
Cumulative planned to that month |  |  | 605000
Cumulative earned |  |  | 555000
Cumulative actual cost |  |  | 590000
Schedule index SPI |  |  | 0.91736
Cost index CPI |  |  | 0.94068
Progress vs. total planned |  |  | 50.45%

## Guide
How to use: Project S-Curve & Cash Flow
Sheetaky.com · Ready Excel sheets in Arabic and English
What is this sheet?
The sheet draws the project S-curve from monthly values: planned (PV), earned (EV) and actual cost (AC). It calculates cumulative values, percentages and the schedule and cost indices up to the last month you entered, for up to 24 months.
Steps
1 | Enter the project start month (any day of that month).
2 | Enter the planned value for each month from the cost-loaded schedule.
3 | Each month, add the value of work done (earned) and the actual cost for that month.
4 | Read the curve: earned below planned means delay, actual above earned means cost overrun.
Color legend
Input cell: type or choose your value here (blue text on yellow).
Calculated cell: automatic formula, protected from accidental edits.
Table and section headers.
Important notes
• | Leave future months empty in the earned and actual columns so they do not show on the curve.
• | Sheets are protected without a password to keep formulas safe. To unprotect: Review → Unprotect Sheet.
• | The data shown is a worked example. Clear it and type your own data in the yellow cells only.
• | More free sheets in Arabic and English at Sheetaky.com