## Punch List
Punch List: Tracking Defect Closure Before Handover
Log each defect with an owner and priority; get due dates, delays and handover readiness
[12 empty] | Discipline |  | Open
Settings |  |  |  | Total items |  | Closed % |  | Open |  | Overdue |  | Architectural
Report date |  | 2026-10-23 | [9 empty] | Structural
Max open items for handover |  | 5 | [9 empty] | Electrical
HVAC
Plumbing
|  |  |  | By responsible |  |  |  | Total | Open | Late | Closed % | Finishes and paint
External works
[12 empty] | Priority | SLA days
[12 empty] | High | 3
[12 empty] | Medium | 7
[12 empty] | Low | 14
Oldest open item (days)
|  |  |  | Max age | [7 empty] | Status
|  |  |  | Avg age of open items | [7 empty] | Open
In progress
Fixed, awaiting check
List | [11 empty] | Closed
# | Location | Discipline | Description | Priority | Responsible | Raised | Due | Status | Closed | Age (d) | Flag
1 | Villa 1 - Living | Finishes and paint | Cracked paint on north wall | High | Modern Paints | 2026-10-05 |  | Closed | 2026-10-13 |  |  | Responsible
2 | Villa 1 - Kitchen | Plumbing | Floor drain slope insufficient | Medium | National Plumbing | 2026-10-08 |  | In progress |  |  |  | Modern Paints
3 | Villa 1 - Bedroom | Electrical | Light switch not working | Low | United Electric | 2026-10-11 |  | Closed | 2026-10-14 |  |  | United Electric
4 | Villa 1 - Bathroom | Plumbing | Leak from shower mixer | High | National Plumbing | 2026-10-13 |  | Open |  |  |  | First Builders
5 | Villa 2 - Facade | Finishes and paint | External paint colour mismatch | Medium | Modern Paints | 2026-10-14 |  | Fixed, awaiting check |  |  |  | Gulf HVAC
6 | Villa 2 - Corridor | HVAC | AC grille loosely fixed | Low | Gulf HVAC | 2026-10-15 |  | Closed | 2026-10-18 |  |  | National Plumbing
7 | Villa 2 - Majlis | Architectural | Cracked tile at door | Medium | First Builders | 2026-10-16 |  | Fixed, awaiting check
8 | Villa 2 - Roof | Structural | Water ponding on roof | High | First Builders | 2026-10-17 |  | In progress
9 | Villa 3 - Garden | External works | Uneven path paving | Low | First Builders | 2026-10-18 |  | Open
10 | Villa 3 - Living | Electrical | Socket without cover plate | Low | United Electric | 2026-10-19 |  | Closed | 2026-10-22
11 | Villa 3 - Kitchen | HVAC | Noisy extractor fan | Medium | Gulf HVAC | 2026-10-20 |  | In progress
12 | Villa 3 - Bathroom | Finishes and paint | Tile joints without silicone | Low | First Builders | 2026-10-21 |  | Open
13 | Villa 1 - Stairs | Architectural | Loose handrail | High | First Builders | 2026-10-01 |  | Closed | 2026-10-11
14 | Villa 2 - Bedroom | Architectural | Door does not close properly | Low | Modern Paints | 2026-10-12 |  | Fixed, awaiting check
15 | Villa 3 - Facade | Finishes and paint | Hairline cracks in plaster | Medium | First Builders | 2026-10-22 |  | Open

## Guide
How to use: Punch list
Sheetaky.com · Ready Excel sheets in Arabic and English
What is this sheet?
Tracks snag and defect items before handover: owner, priority, due date, delay and readiness for handover.
Steps
1 | Enter the report date and the maximum open items at handover.
2 | Log each item with location, discipline, description, priority, owner and raised date.
3 | The due date is computed from the priority in the SLA table.
4 | Update status and close date and watch handover readiness.
Color legend
Input cell: type or choose your value here (blue text on yellow).
Calculated cell: automatic formula, protected from accidental edits.
Table and section headers.
Important notes
• | SLA days per priority are editable in the right-hand list.
• | Closed items turn grey.
• | Readiness requires no open high-priority items and open items within the limit.
• | Sheets are protected without a password to keep formulas safe. To unprotect: Review → Unprotect Sheet.
• | The data shown is a worked example. Clear it and type your own data in the yellow cells only.
• | More free sheets in Arabic and English at Sheetaky.com