## BOQ
Subcontractor Certificate by BOQ: Claimed vs Certified, with Back-charges
Enter the subcontractor claimed quantity and the engineer certified quantity; the sheet works out the difference and the amount due after deductions
Item | Description | Unit | Contract qty | Unit rate | Contract amount | Previous certified (cum.) | Claimed now (cum.) | Certified now (cum.) | Certified % | Certified qty this period | Certified value to date | Previous certified value | This period value | Claimed value | Claim − certified
1.1 | General excavation for foundations | m³ | 450 | 18 |  | 450 | 472.5 | 450
1.2 | Compacted backfill | m³ | 300 | 22 |  | 180 | 270 | 255
2.1 | Plain concrete | m³ | 40 | 380 |  | 40 | 42 | 40
2.2 | Reinforced concrete | m³ | 260 | 520 |  | 143 | 215.8 | 202.8
2.3 | Reinforcement steel | ton | 30 | 2600 |  | 16.5 | 24.9 | 23.4
2.4 | Formwork | m² | 1500 | 48 |  | 825 | 1275 | 1200
3.1 | Blockwork 20 cm | m² | 1900 | 62 |  | 570 | 1140 | 1045
3.2 | Internal and external plaster | m² | 4200 | 28 |  | 420 | 1470 | 1260
3.3 | Floor tiles | m² | 1100 | 85 |  | 0 | 165 | 110
3.4 | Paint | m² | 4800 | 16 |  | 0 | 0 | 0
4.1 | Electrical points | point | 320 | 140 |  | 64 | 128 | 112
4.2 | Plumbing points | point | 120 | 190 |  | 24 | 54 | 48
4.3 | Aluminium windows | m² | 210 | 520 |  | 0 | 63 | 52.5
4.4 | Doors | no. | 36 | 780 |  | 0 | 0 | 0
Total
Yellow: claim above certified. Red: certified below previous. Orange: certified above contract quantity.

## Certificate
Subcontractor payment certificate
Subcontractor Certificate by BOQ: Claimed vs Certified, with Back-charges
Contract data
Certificate no. | 3
Certificate date | 2026-08-31
Payment term after certificate (days) | 60
Due date
Value and work
Original subcontract value
Approved variations (net) | 8000
Revised value
Certified work to date
Certified variation work to date | 3000
Gross value to date
Deductions
Retention rate % | 10%
Retention to date
Retention released | 0
Advance paid | 60000
Advance recovered to date (pro rata)
Main contractor back-charges
Description | Amount
Materials supplied by main contractor (cement) | 6200
Site power and water | 1800
Cleaning and waste removal | 1200
Total back-charges
Delay damages | 0
Net amount due
Net certified to date
Previously paid (net) | 90000
Net of this certificate before VAT
VAT rate | 15%
VAT amount
Payable incl. VAT
Claim versus certified
Subcontractor claim (cumulative)
Difference: claim − certified
Certified as % of claim
Financial progress

## Guide
How to use: Subcontractor Certificate by BOQ: Claimed vs Certified, with Back-charges
Sheetaky.com · Ready Excel sheets in Arabic and English
What is this sheet?
A subcontractor certificate by bill of quantities: the subcontractor enters the cumulative claimed quantity and the engineer enters the certified quantity, which shows the difference between them. The sheet then works out certified value, retention and its release, advance recovery, main-contractor back-charges and damages, the net amount due and its due date.
Steps
1 | Enter the subcontract items, quantities and rates in the "BOQ" sheet.
2 | For each item enter the previous certified, current claimed and current certified quantities (all cumulative).
3 | In the "Certificate" sheet enter variations, retention, advance payment, the back-charges table and damages.
4 | Enter what was paid previously to get the net of this certificate, the amount incl. VAT and the due date.
Color legend
Input cell: type or choose your value here (blue text on yellow).
Calculated cell: automatic formula, protected from accidental edits.
Table and section headers.
Important notes
• | Certified must not fall below the previous quantity (red) nor exceed the contract quantity without a variation (orange).
• | Back-charges are entered as positive amounts and are deducted automatically.
• | If your contract imposes withholding tax or different retention terms, edit the formulas accordingly.
• | Sheets are protected without a password to keep formulas safe. To unprotect: Review → Unprotect Sheet.
• | The data shown is a worked example. Clear it and type your own data in the yellow cells only.
• | More free sheets in Arabic and English at Sheetaky.com