## Certificates
Subcontractor Payment Certificates Tracker
Work done, retention, advance recovery, VAT, paid and outstanding
Contract details
Subcontractor |  |  | Al Itqan Contracting
Scope |  |  | Blockwork and plaster
Contract value excl. VAT |  |  | 480000
Retention |  |  | 10%
Advance payment (% of contract) |  |  | 10%
Recovery rate per certificate |  |  | 15%
VAT rate |  |  | 15%
Advance amount |  |  | 48000
Certificates log
No. | Cert. date | Cumulative work done | This period | Retention | Advance recovery | Net before VAT | VAT | Amount due | Paid | Paid on | Outstanding
1 | 2026-03-31 | 72000 | 72000 | 7200 | 10800 | 54000 | 8100 | 62100 | 62100 | 2026-04-20 | 0
2 | 2026-04-30 | 165000 | 93000 | 9300 | 13950 | 69750 | 10462.5 | 80212.5 | 60000 |  | 20212.5
3 | 2026-05-31 | 262000 | 97000 | 9700 | 14550 | 72750 | 10912.5 | 83662.5 |  |  | 83662.5
4 | 2026-06-30 | 341000 | 79000 | 7900 | 8700 | 62400 | 9360 | 71760 |  |  | 71760
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Total |  |  | 341000 | 34100 | 48000 | 258900 | 38835 | 297735 | 122100 |  | 175635
Summary
Work done to date |  |  | 341000
Financial progress |  |  | 71.04%
Retention held |  |  | 34100
Advance still to recover |  |  | 0
Total due incl. VAT |  |  | 297735
Total paid |  |  | 122100
Outstanding |  |  | 175635
Contract value remaining |  |  | 139000
This period = current cumulative − highest previous cumulative. Recovery = recovery rate × this period, capped at the advance still due. Red: a cumulative lower than before.

## Guide
How to use: Subcontractor Payment Certificates Tracker
Sheetaky.com · Ready Excel sheets in Arabic and English
What is this sheet?
A tracker for subcontractor payment certificates: enter the cumulative work done on each certificate and it calculates this period, retention, advance recovery, VAT and the amount due; record what you paid to see the outstanding balance, with a summary, progress and a chart.
Steps
1 | Enter the contract details: value, retention, advance, recovery and VAT rates.
2 | For each certificate enter its number, date and the cumulative work done to date.
3 | When you pay, enter the amount and the date.
4 | Check the summary: retention held, advance to recover, paid and outstanding.
Color legend
Input cell: type or choose your value here (blue text on yellow).
Calculated cell: automatic formula, protected from accidental edits.
Table and section headers.
Important notes
• | Retention is usually released at practical or final completion per the contract; record its release as a separate payment.
• | Sheets are protected without a password to keep formulas safe. To unprotect: Review → Unprotect Sheet.
• | The data shown is a worked example. Clear it and type your own data in the yellow cells only.
• | More free sheets in Arabic and English at Sheetaky.com