## Variations
Variation Orders Log: Value, Status and Impact on Contract and Time
Log every variation with value, status and time; see its net impact on the contract value and duration and what is awaiting approval
Variation register
No. | Description | Type | Qty | Unit | Rate | Value (±) | Status | Time claimed (days) | Time approved (days) | Contract data
VO-01 | Change hall tiles to porcelain | Addition | 180 | m² | 45 |  | Approved | 0 | 0 | Original contract value | 925680
VO-02 | Omit rear garden wall | Omission | 60 | m | 320 |  | Approved | 0 | 0 | Original duration (days) | 365
VO-03 | Add rooftop services room | Addition | 1 | lump sum | 38000 |  | Approved | 12 | 12
VO-04 | Relocate electrical points | Addition | 24 | point | 140 |  | Approved | 0 | 0 | Impact on the contract
VO-05 | Strengthen north footings | Addition | 14 | m³ | 560 |  | Pending | 7 | 0 | Approved additions
VO-06 | Change external paint specification | Addition | 900 | m² | 9 |  | Pending | 0 | 0 | Approved omissions
VO-07 | Add entrance canopy | Addition | 1 | lump sum | 16500 |  | Rejected | 5 | 0 | Net approved
VO-08 | Omit second balcony balustrade | Omission | 18 | m | 210 |  | Approved | 0 | 0 | Revised contract value
Change as % of contract
Pending net exposure
Rejected (net)
Impact on time
Time approved (days)
Time pending (days)
Revised duration (days)
Counts
Approved
Pending
Rejected

## Guide
How to use: Variation Orders Log: Value, Status and Impact on Contract and Time
Sheetaky.com · Ready Excel sheets in Arabic and English
What is this sheet?
A log of project variation orders: each has a description, type (addition or omission), quantity, rate, status (pending, approved or rejected) and time claimed and approved. The sheet totals what is approved, what awaits a decision and what was rejected, and works out the revised contract value, the percentage change and the revised duration.
Steps
1 | Enter the original contract value and duration in the side panel.
2 | Register each variation in a row: description, type, quantity, rate and status.
3 | When approved change the status to "Approved" and enter the approved time.
4 | Check the revised contract value and the pending amounts before each certificate and carry the net approved into the certificate.
Color legend
Input cell: type or choose your value here (blue text on yellow).
Calculated cell: automatic formula, protected from accidental edits.
Table and section headers.
Important notes
• | Omissions are recorded as negative values automatically.
• | Yellow is pending, green approved and red rejected.
• | Pending orders are a financial exposure; follow them up regularly.
• | Sheets are protected without a password to keep formulas safe. To unprotect: Review → Unprotect Sheet.
• | The data shown is a worked example. Clear it and type your own data in the yellow cells only.
• | More free sheets in Arabic and English at Sheetaky.com