## Wedding Dashboard
Wedding and Honeymoon Dashboard: Budget, Guests and Deadlines
Everything for the big day on one page: what you paid, what remains, who confirmed and which tasks are late
|  |  |  | Next payments | Due | Balance | In days
Wedding date | 2027-04-15 | days to the wedding
Today | 2026-10-23
Total budget | 120000
Venue capacity | 250
Committed | Paid | Balance due | Vs budget
|  |  |  | Category | Committed | Paid | %
Invited people | Confirmed | Pending | Declined
Wedding cost / confirmed guest | Honeymoon total | Overdue tasks | Tasks done

## Budget
Wedding and Honeymoon Budget
Enter estimate, contracted price, paid amount and next payment date for each item
Item | Vendor | Category | Group | Estimate | Contract | Paid | Committed | Balance | Next due | Key | Category
Wedding hall | Al Fustan Hall | Venue & catering | Wedding | 18000 | 17500 | 8000 |  |  | 2026-11-12 |  | Venue & catering
Catering | Al Diyar Kitchens | Venue & catering | Wedding | 21250 | 22000 | 5000 |  |  | 2026-12-07 |  | Attire & beauty
Photo & video | Lamha Studio | Photo & decor | Wedding | 6000 | 5500 | 2000 |  |  | 2026-12-22 |  | Photo & decor
Bride dress | Elegance Boutique | Attire & beauty | Wedding | 9000 | 9800 | 9800 |  |  |  |  | Entertainment & transport
Groom bisht & suit | Tailor House | Attire & beauty | Wedding | 2500 | 2500 | 1000 |  |  | 2026-11-22 |  | Travel & stay
Wedding rings | Al Noor Jewellery | Attire & beauty | Wedding | 7500 | 7200 | 7200 |  |  |  |  | Activities & other
Invitations | Art Printing | Photo & decor | Wedding | 1800
Decor & flowers | Lamasat | Photo & decor | Wedding | 8000 | 8500 | 3000 |  |  | 2026-12-12
Band & zaffa | Farah Band | Entertainment & transport | Wedding | 3500 | [6 empty] | Group
Makeup & hair | Reem Salon | Attire & beauty | Wedding | 2200 | [6 empty] | Wedding
Sweets & favours | Sham Sweets | Venue & catering | Wedding | 3000 | [6 empty] | Honeymoon
Wedding cars | Riyadh Limo | Entertainment & transport | Wedding | 1500
Flights | Airline | Travel & stay | Honeymoon | 9500 | 9100 | 9100
Honeymoon hotel | Island Resort | Travel & stay | Honeymoon | 12000 | 11500 | 4000 |  |  | 2026-11-17
Activities & tours | Pre-booked | Activities & other | Honeymoon | 3000
Insurance & visas | Insurer | Activities & other | Honeymoon | 800
Spending money | - | Activities & other | Honeymoon | 5000

## Guests
Guest List
Log each family or group with its size and reply
# | Guest / group | Side | Size | RSVP | Table | RSVP
1 | Al-Otaibi family | Groom | 2 | Yes | 1 | Yes
2 | Al-Harbi family | Bride | 4 | Yes | 1 | No
3 | Al-Qahtani family | Groom | 6 | Yes | 1 | Pending
4 | Al-Shammari family | Bride | 3 | No
5 | Al-Dosari family | Groom | 5 | Pending
6 | Al-Zahrani family | Bride | 8 | Yes | 2 | Side
7 | Al-Mutairi family | Groom | 2 | No |  | Groom
8 | Al-Subaie family | Bride | 4 | Yes | 2 | Bride
9 | Al-Anazi family | Groom | 6 | No
10 | Al-Ghamdi family | Bride | 3 | Pending
11 | Al-Buqami family | Groom | 7 | Yes | 3
12 | Al-Juhani family | Bride | 4 | Yes | 3
13 | Work friends | Groom | 5 | Yes | 3
14 | School friends | Bride | 3 | No
15 | Neighbours | Groom | 4 | Pending
16 | Al-Shehri family | Bride | 6 | Yes | 4
17 | Al-Omari family | Groom | 2 | Yes | 4
18 | Al-Rashidi family | Bride | 5 | Yes | 4
19 | Al-Sahli family | Groom | 4 | No
20 | Al-Hazmi family | Bride | 3 | Pending
21 | Al-Thubaiti family | Groom | 6 | No
22 | Al-Maliki family | Bride | 4 | Yes | 5
23 | Team colleagues | Groom | 5 | Yes | 5
24 | Al-Khalidi family | Bride | 3 | No
25 | Al-Fahad family | Groom | 8 | Pending
26 | Al-Nemer family | Bride | 4 | Yes | 6
27 | Al-Balawi family | Groom | 2 | Yes | 6
28 | Al-Yami family | Bride | 5 | No
29 | Al-Tamimi family | Groom | 6 | No
30 | Al-Saedi family | Bride | 3 | Pending

## Tasks
Planning Timeline
Every task has a deadline in months before the wedding; tick ✔ when done
Task | Months before | Due date | Done | Status
Book the venue | 12 |  | ✔
Choose the photographer | 9 |  | ✔
Book flights | 8 |  | ✔
Order dress and suit | 6 |  | ✔
Send invitations | 3 |  | ✔
Confirm the guest list | 2
Makeup trial | 1.5
Settle vendor balances | 1
Confirm hotel booking | 1
Pack for the trip | 0.5

## Guide
How to use: Wedding dashboard
Sheetaky.com · Ready Excel sheets in Arabic and English
What is this sheet?
Combines the wedding and honeymoon budget, guest list and planning timeline on one board, showing committed, paid, balance, upcoming payments, cost per guest and venue capacity.
Steps
1 | Enter the wedding date, budget and venue capacity.
2 | Record each item on the budget sheet with estimate, contract and paid.
3 | Add guests and replies on the guest sheet.
4 | Tick ✔ when a task is done.
Color legend
Input cell: type or choose your value here (blue text on yellow).
Calculated cell: automatic formula, protected from accidental edits.
Table and section headers.
Important notes
• | Committed = contract price if present, otherwise the estimate.
• | Cost per guest = wedding commitments ÷ confirmed guests.
• | Task due date = wedding date − months × 30.4.
• | Sheets are protected without a password to keep formulas safe. To unprotect: Review → Unprotect Sheet.
• | The data shown is a worked example. Clear it and type your own data in the yellow cells only.
• | More free sheets in Arabic and English at Sheetaky.com